## gantt chart
Project: Shared Sounds
William Booth -- 2302168
Project start date: | 2024-01-01
[5 empty] | January | [30 empty] | February
[5 empty] | 2024-01-01 | 2024-01-02 | 2024-01-03 | 2024-01-04 | 2024-01-05 | 2024-01-06 | 2024-01-07 | 2024-01-08 | 2024-01-09 | 2024-01-10 | 2024-01-11 | 2024-01-12 | 2024-01-13 | 2024-01-14 | 2024-01-15 | 2024-01-16 | 2024-01-17 | 2024-01-18 | 2024-01-19 | 2024-01-20 | 2024-01-21 | 2024-01-22 | 2024-01-23 | 2024-01-24 | 2024-01-25 | 2024-01-26 | 2024-01-27 | 2024-01-28 | 2024-01-29 | 2024-01-30 | 2024-01-31 | 2024-02-01 | 2024-02-02 | 2024-02-03 | 2024-02-04 | 2024-02-05 | 2024-02-06 | 2024-02-07 | 2024-02-08 | 2024-02-09
Milestone description |  | Progress | Start | Days | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F
Project development
Project name |  | 80% | 2024-01-01 | 1
Create gantt chart |  | 20% | 2024-01-01 | 1
Identify tarket audience |  | 100% | 2024-01-02 | 1
Project requirements |  | 20% | 2024-01-12 | 3
Notes for abstract |  | 50% | 2024-01-13 | 6
Wireframe |  | 0% | 2024-01-17 | 2
Create Spotify API token |  | 100% | 2024-01-18 | 1
Basic boilerplate code |  | 100% | 2024-01-18 | 1
Write abstract |  | 0% | 2024-01-19 | 21
Testing
Design and run tests |  | 0%
Get feedback |  | 0%
Implement feedback |  | 0%
Documentation
Document for writeup |  | 0%
Refrencing |  | 0%
Submit project |  | 0%